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	Key focus Programme
	Pillars
	Responsible institutions(s)
	Timelines
	Budget

	Sector support
	Support for 10 key priority sectors and designated sectors
	All GPG department and entities
	2022 -2025
	R20 million 

	Financial support
	The Cooperatives Loan Fund
	GEP, SEDA and SEFA 
	2021 - 2025
	R10 million

	
	Covid-19 Relieve Fund
	GEP
	2021 - 2025
	From the R100 million Covid-19 Fund

	
	The hosting of a bi-annual Funding Fair Programme for Cooperatives 
	GEP, GDED and Treasury
	2022 - 2025
	R50 000 annually

	
	Bi-Annual Investment Readiness Programme
	GEP and Treasury
	2022 - 2025
	R100 000 annually

	
	Cooperatives Contract Fund 
	GEP
	2022 - 2025
	R15 million

	
	The Cooperative Incentive Scheme 
	DSBD
	2022 - 2025
	Under review

	
	Community Grant
	GEP
	2021 - 2025
	R13.5 million

	
	Cooperatives Finance Institutions
	GDED 
	2021 - 2025
	R5 million

	
	Cooperatives Bank
	GDED
	2021 - 2025
	

	
	Support Grant Programme
	NYDA
	2021 - 2025
	R1 million

	
	Promotion of exports
	GGDA
	2023 - 2025
	R1 million

	Non-financial support
	Mentorship Programme 
	GEP
	On-going 
	R1 million

	
	Technology Support 
	GEP and The Innovation Hub
	On-going
	R1 million

	
	Quality & Standards 
	GEP and SABS
	2022 - 2025
	R10 million

	
	Production infrastructure 
	GEP and GDED
	On-going
	R15 million

	
	Machinery and equipment 
	GEP and DSBD
	On-going
	R10 million

	Creating demand for goods and services produced by cooperatives
	Access to markets in the public sector through 5% budget set aside 
	All GPG Departments and Agencies
	2022 - 2025
	5% procurement set aside budget 

	
	Access to markets in the private sector
	GEP and GDED
	2022 - 2025
	N/A

	Promote Graduate and Youth Cooperatives
	Information Technology and smart industries
	e-Government, GPT, 
Innovation Hub and GEP
	2022 - 2025
	R10 million

	
	Manufacturing
	
	
	

	
	Research and development
	GEP and GDED
	2022 - 2025
	R5 million

	Education 
	Establishment of Cooperatives College/ partnership with institutions of higher learning to establish a Cooperative Centre for training 
	GDED (to coordinate), the OoP, DSBD and NYDA to facilitate the signing of MOU with institutions of higher learning
	2022 - 2025
	R10 million

	
	National and International Exchange Programme for Cooperatives
	Cooperatives and GEP on 50:50 cost sharing basis for Local Exchange Programmes.
	2023 - 2025
	R3 million

	
	
	GDED for International Exchange Programme
	2023 - 2025
	

	Policy Advocacy and Coordination 
	Cooperatives Forums across government
	GDED and GEP
	Quarterly
	R200 000

	
	Bi-annual Provincial Policy Forums
	
	Bi-annually
	R200 000

	
	Inter-Provincial Policy Forum
	
	Quarterly
	R200 000

	
	Municipal Working Session and IDP Week
	
	Quarterly
	R200 000

	
	Provincial Cabinet Committee
	
	Quarterly
	R200 000





